## Day-Wise Work Plan
SCALEZIX VENTURES LLP — OfficeX Web Platform (Phase 1) — Day-Wise Plan
60 Working Days (Mon-Sat) ¦ Starts 20-Aug-2026 ¦ Sequence begins with UI/UX & System Structure
Day | Date | Day of Week | Phase | Task / Activity | Key Deliverable / Output | Milestone / Payment | Status
1 | 2026-08-20 | Thursday | UI/UX & Structure | Kickoff call with OfficeX (Prabhat Ji) — confirm business workflows, user roles, data fields; begin Information Architecture | Kickoff |  | In Progress
2 | 2026-08-21 | Friday | UI/UX & Structure | Portal structure finalisation — 9 portals: Public, Leasing, FM Marketplace, Property Mgmt, Vendor, Client, Admin, Ops, Reporting | Portal Structure Map |  | Not Started
3 | 2026-08-22 | Saturday | UI/UX & Structure | Core screen wireframes — Property discovery, listing, search & leasing screens | Wireframes Set 1 |  | Not Started
4 | 2026-08-24 | Monday | UI/UX & Structure | Core screen wireframes — FM Marketplace, RFQ, quotation & work order screens | Wireframes Set 2 |  | Not Started
5 | 2026-08-25 | Tuesday | UI/UX & Structure | Core screen wireframes — Property Management, SaaS modules (assets, tickets, rent roll, compliance) | Wireframes Set 3 |  | Not Started
6 | 2026-08-26 | Wednesday | UI/UX & Structure | Navigation structure & role-based dashboard layouts (Mgmt / Property Mgr / Facility Mgr / Vendor) | Dashboard UI Structure |  | Not Started
7 | 2026-08-27 | Thursday | UI/UX & Structure | User workflow mapping — leasing pipeline, FM procurement flow, ticket/SLA flow, AI assistant flow | User Workflow Maps |  | Not Started
8 | 2026-08-28 | Friday | UI/UX & Structure | UI/UX review call with OfficeX, incorporate feedback, sign-off; finalise RBAC matrix & Scope Baseline docs in parallel | UI/UX Sign-off + Scope Freeze |  | Not Started
9 | 2026-08-29 | Saturday | Core Platform | Set up Git repository (OfficeX-owned), Dev/Staging/Production environments, CI/CD pipeline | Repo + Environments Live |  | Not Started
10 | 2026-08-31 | Monday | Core Platform | Secure authentication module (role-based login, password hashing) | Auth Module |  | Not Started
11 | 2026-09-01 | Tuesday | Core Platform | Roles & permissions engine — RBAC table (role -> module -> action) | RBAC Engine |  | Not Started
12 | 2026-09-02 | Wednesday | Core Platform | Database schema design (PostgreSQL/Supabase) & core data model | Data Dictionary + DB Schema |  | Not Started
13 | 2026-09-03 | Thursday | Core Platform | Admin portal foundation — Users & Properties master modules | Admin Portal (Users/Properties) |  | Not Started
14 | 2026-09-04 | Friday | Core Platform | Admin portal foundation — Vendors & Clients master modules | Admin Portal (Vendors/Clients) |  | Not Started
15 | 2026-09-05 | Saturday | Core Platform | Documents module — secure cloud file/object storage & association logic | Document Storage Module |  | Not Started
16 | 2026-09-07 | Monday | Core Platform | Core REST/JSON APIs — API-first architecture for all master entities | Core APIs |  | Not Started
17 | 2026-09-08 | Tuesday | Core Platform | Audit Trail module (action, user/admin, timestamp, record affected) | Audit Trail Module |  | Not Started
18 | 2026-09-09 | Wednesday | Core Platform | Core platform integration testing & internal review before module build begins | Core Platform QA Pass |  | Not Started
19 | 2026-09-10 | Thursday | Property & Leasing | Property listing management module (create/edit listings, all property fields) | Property Listing Module |  | Not Started
20 | 2026-09-11 | Friday | Property & Leasing | Public property search & discovery with filters (location, type, rent, amenities) | Property Search Module |  | Not Started
21 | 2026-09-12 | Saturday | Property & Leasing | Property enquiry & lead management — receive, assign, track leads | Lead Management Module |  | Not Started
22 | 2026-09-14 | Monday | Property & Leasing | Lead pipeline automation — Enquiry to Qualified to Site Visit to Negotiation to LOI to Lease to Closed | Lead Pipeline Engine |  | Not Started
23 | 2026-09-15 | Tuesday | Property & Leasing | Site visit management — scheduling, feedback, follow-up tracking | Site Visit Module |  | Not Started
24 | 2026-09-16 | Wednesday | Property & Leasing | LOI & lease workflow — Property Selected to Negotiation to LOI to Documentation | LOI Workflow Module |  | Not Started
25 | 2026-09-17 | Thursday | Property & Leasing | Lease execution & document tracking; deal status management | Lease Execution Module |  | Not Started
26 | 2026-09-18 | Friday | Property & Leasing | Brokerage & leasing commission tracking (transaction value, invoice, payment status) | Brokerage Commission Module |  | Not Started
27 | 2026-09-19 | Saturday | FM Marketplace | Vendor registration & profile management (GST/PAN, licences, geography, categories) | Vendor Portal (Registration) |  | Not Started
28 | 2026-09-21 | Monday | FM Marketplace | Vendor verification workflow — Registered to Documents Submitted to Review to Verified/Rejected | Vendor Verification Module |  | Not Started
29 | 2026-09-22 | Tuesday | FM Marketplace | RFQ management — creation, service scope, requirement, submission deadlines | RFQ Module |  | Not Started
30 | 2026-09-23 | Wednesday | FM Marketplace | RFQ eligible-vendor selection logic & vendor participation flow | RFQ Vendor Matching |  | Not Started
31 | 2026-09-24 | Thursday | FM Marketplace | Vendor quotation submission module (price, taxes, scope, terms, documents) | Quotation Module |  | Not Started
32 | 2026-09-25 | Friday | FM Marketplace | Quotation comparison module (vendor, price, verification, rating, SLA, terms) | Quotation Comparison Module |  | Not Started
33 | 2026-09-26 | Saturday | FM Marketplace | Work order management — Draft to Issued to Accepted to In Progress to Completed to Closed | Work Order Module |  | Not Started
34 | 2026-09-28 | Monday | FM Marketplace | Vendor ratings & marketplace commission engine (configurable %, tax treatment) | Ratings + Commission Module | Phase 1 Completion (50%) Payment | Not Started
35 | 2026-09-29 | Tuesday | Property/FM Ops | Property Management module — property master, owner/tenant/lease/asset/rent overview | Property Management Portal |  | Not Started
36 | 2026-09-30 | Wednesday | Property/FM Ops | Managed Services Delivery — contract management (client, property, SLA, service categories) | Managed Services Module (Contracts) |  | Not Started
37 | 2026-10-01 | Thursday | Property/FM Ops | Managed Services — daily/site activity logging (activities, issues, completed/pending tasks) | Daily Activity Module |  | Not Started
38 | 2026-10-02 | Friday | Property/FM Ops | Attendance management for managed contracts | Attendance Module |  | Not Started
39 | 2026-10-03 | Saturday | Property/FM Ops | SLA monitoring & tracking (define, track service-level obligations) | SLA Monitoring Module |  | Not Started
40 | 2026-10-05 | Monday | Property/FM Ops | 52-week Planned Preventive Maintenance (PPM) calendar module | PPM Calendar Module |  | Not Started
41 | 2026-10-06 | Tuesday | Property/FM Ops | Monthly MIS reporting engine (activities, SLA, tickets, PPM, attendance, vendor performance) | MIS Reporting Module |  | Not Started
42 | 2026-10-07 | Wednesday | Property/FM Ops | Property/FM Operations module integration testing | Ops Module QA Pass |  | Not Started
43 | 2026-10-08 | Thursday | SaaS Modules | Asset register module (asset ID, category, warranty, AMC, assigned vendor) | Asset Register Module |  | Not Started
44 | 2026-10-09 | Friday | SaaS Modules | Ticketing & Helpdesk module — Open to Assigned to In Progress to Resolved to Closed | Ticketing Module |  | Not Started
45 | 2026-10-10 | Saturday | SaaS Modules | Rent Roll management module (property, unit, tenant, lease, rent, escalation) | Rent Roll Module |  | Not Started
46 | 2026-10-12 | Monday | SaaS Modules | Rent collection tracking (due date, paid/outstanding amount, payment status) | Rent Collection Module |  | Not Started
47 | 2026-10-13 | Tuesday | SaaS Modules | Tenant management module (organisation, contacts, occupied space, documents) | Tenant Management Module |  | Not Started
48 | 2026-10-14 | Wednesday | SaaS Modules | Visitor management module (registration, host, approval, entry/exit status) | Visitor Management Module |  | Not Started
49 | 2026-10-15 | Thursday | SaaS Modules | Compliance management, document storage & expiry tracking (Valid to Expiring to Expired to Renewed) | Compliance Module |  | Not Started
50 | 2026-10-16 | Friday | SaaS Modules | Notifications & Alerts engine (RFQ, SLA, PPM, rent due, compliance expiry) + role-based Dashboards/Analytics | Notifications + Dashboards Module |  | Not Started
51 | 2026-10-17 | Saturday | AI & Payments | OfficeX AI Assistant foundation — natural-language interface over structured platform data | AI Assistant Foundation |  | Not Started
52 | 2026-10-19 | Monday | AI & Payments | AI-assisted vendor recommendation foundation & AI ticket intelligence (classification, priority, routing) | AI Vendor + Ticket Intelligence |  | Not Started
53 | 2026-10-20 | Tuesday | AI & Payments | AI MIS/operational summaries, AI document intelligence foundation, Energy & ESG data foundation | AI Automation Layer (complete) |  | Not Started
54 | 2026-10-21 | Wednesday | AI & Payments | Payment gateway integration — Razorpay Orders API, Checkout, webhook verification & reconciliation job | Payments Integration Live |  | Not Started
55 | 2026-10-22 | Thursday | Testing | Functional testing & workflow testing across all 17 modules | Internal QA Pass 1 |  | Not Started
56 | 2026-10-23 | Friday | Testing | Role/permission (RBAC data-boundary) testing & baseline security checks — input validation, RBAC, HTTPS | Security Baseline Report |  | Not Started
57 | 2026-10-24 | Saturday | Testing | Integration testing — Razorpay, Google Maps, SMS, WhatsApp, Email, AI API | Integration Test Report |  | Not Started
58 | 2026-10-26 | Monday | Testing | Internal bug-fix pass & regression check before UAT hand-off | Pre-UAT Build |  | Not Started
59 | 2026-10-27 | Tuesday | Deployment | Staging deployment & User Acceptance Testing (UAT) kickoff with OfficeX | Staging Live + UAT Kickoff |  | Not Started
60 | 2026-10-28 | Wednesday | Deployment | Production configuration, database deployment, final verification & GO-LIVE | PRODUCTION GO-LIVE | Post-Deployment Payment 34% due (up to 6% hold-back pending sign-off) - | Not Started
Note: 2-week post-go-live buffer (stabilisation, UAT closure, training & handover, final sign-off, hold-back release) follows Day 60 and is tracked separately once go-live is confirmed.