## Pending & 7-Day Plan
OFFICEX.PRO — PENDING PLATFORM FEATURES & 7-DAY DELIVERY ROADMAP
Current Status: Today is 21-Oct-2026 ¦ Scope: Whole OfficeX Platform ¦ Target Go-Live: Tuesday, 27-Oct-2026
1. FEATURES CURRENTLY IN TESTING (QA PASS) — 11 Deliverables (Verification & Sign-Off)
Portal / Domain | Feature / Flow Name | Functionality & User Flow | Current Status | Target Timeline
Rent Roll & Landlord SaaS | Visual Stacking Plan & Floor Occupancy Matrix | Interactive floor-by-floor building elevation displaying occupied vs vacant units, square footage, and tenant badges. | IN TESTING | Day 2 (22-Oct-2026)
Rent Roll & Landlord SaaS | Dual-Authorization Maker-Checker Approval Rules | Dual sign-off enforcement preventing makers from self-authorizing; checker approval audit logging on lease edits and invoices. | IN TESTING | Day 2 (22-Oct-2026)
Commercial Leasing CRM | Inbound Tenant Lead Triage Desk | Intake queue qualifying incoming commercial tenant inquiries, capturing space budget, required sqft, and marketing source. | IN TESTING | Day 2 (22-Oct-2026)
Commercial Leasing CRM | Deals Pipeline Kanban Board | Visual deal stage progression (Inquiry -> Site Visit -> Negotiation -> Term Sheet LOI -> Contract Signed -> Closed). | IN TESTING | Day 2 (22-Oct-2026)
Commercial Leasing CRM | Site Visit Management & Feedback Logs | Scheduling on-site tenant walkthroughs, logging broker follow-ups, and prospective occupier interest feedback. | IN TESTING | Day 2 (22-Oct-2026)
Office Marketplace | 4-Way Commercial Space Spec Comparison | Side-by-side comparison table analyzing monthly rent, CAM charges, furnishing, floor plate, and security deposit terms. | IN TESTING | Day 2 (22-Oct-2026)
Office Marketplace | Calq Space Requirement & Budget Estimator | Interactive calculator deriving required carpet area, linear workstations, cabins, and budget based on employee headcount. | IN TESTING | Day 2 (22-Oct-2026)
FM Marketplace | B2B RFQ Scope Builder & Vendor Auto-Match | Property managers publish maintenance tenders with SLA tags; system automatically matches and notifies eligible vetted vendors. | IN TESTING | Day 2 (22-Oct-2026)
FM Marketplace | Vendor KYC & Document Verification Desk | Admin moderation queue verifying uploaded GSTIN, PAN, PF/ESIC, and insurance certificates to grant verified vendor status. | IN TESTING | Day 2 (22-Oct-2026)
Property & FM Operations | 52-Week Planned Preventive Maintenance (PPM) Calendar | Comprehensive 52-week recurring maintenance calendar for chillers, lifts, DG sets, and fire systems with auto work orders. | IN TESTING | Day 2 (22-Oct-2026)
Rent Roll & Landlord SaaS | Aging Receivables & Collections Tracker | Aged debtors ledger categorizing overdue rent and CAM arrears into 0-30, 31-60, 61-90, and 90+ days aging buckets. | IN TESTING | Day 2 (22-Oct-2026)
2. FEATURES CURRENTLY IN DEVELOPMENT (ACTIVE BUILD) — 11 Deliverables (Scheduled Completion)
Portal / Domain | Feature / Flow Name | Functionality & User Flow | Current Status | Target Timeline
Financials & Invoicing | Automated Monthly Rent Roll Billing Run & Tax Invoices | End-of-month batch billing script generating GST-compliant tax invoices (Base Rent + CAM + GST tax calculation). | IN DEVELOPMENT | Day 3 (23-Oct-2026)
Financials & Invoicing | Utility Sub-Meter Reading & CAM Pro-Rata Allocator | Digital entry table for electricity and water meter readings, calculating slab tariffs and pro-rata tenant CAM splits. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
Payments & Gateway | Razorpay Live Payment Gateway & Virtual Accounts | Integration of Razorpay Orders API for rent collection, unique virtual payment links, and webhook payment settlement. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
FM Marketplace | Quotation Submission & Multi-Vendor Comparison Matrix | Side-by-side comparison matrix for bids submitted by vendors against issued RFQs, highlighting lowest rate and fastest SLA. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
FM Operations SaaS | Work Order Lifecycle & Mandatory Photo Proof Gate | Work order dispatch (Issued -> Accepted -> In Progress -> Closed) requiring mandatory before/after photo upload. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
FM Operations SaaS | Vendor Rating & Marketplace Commission Engine | Post-service vendor 1-5 star ratings, SLA compliance score calculation, and marketplace fee deduction logic. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
Tenant Portal | Tenant Self-Service Statement & Online Invoice Payment | Tenant financial desk to download monthly GST statements, view ledger balances, and settle dues online. | IN DEVELOPMENT | Day 3 (23-Oct-2026)
Commercial Leasing CRM | Digital LOI & Commercial Term Sheet Generator | Automated PDF term sheet generator populating agreed lease parameters with landlord and tenant signature blocks. | IN DEVELOPMENT | Day 4 (24-Oct-2026)
Office Marketplace | Space Listing Partner Submission Builder | Self-service listing builder enabling landlords and brokers to add commercial office inventory with floor plans. | IN DEVELOPMENT | Day 4 (24-Oct-2026)
SaaS Modules | Visitor Management Pre-Invites & QR Code Passes | Host tenants issue digital visitor invitations; visitors receive secure QR passes scanned at security lobby desks. | IN DEVELOPMENT | Day 4 (24-Oct-2026)
SaaS Modules | Statutory Compliance Document Vault with Expiry Alerts | Centralized vault for Fire NOC, Lift Licenses, and Building OC with automated 60/30/15-day expiry warning triggers. | IN DEVELOPMENT | Day 5 (25-Oct-2026)
3. PENDING FEATURES & AI SUITE (100% PENDING AS SCHEDULED) — 10 Deliverables (Days 4 to 7)
Portal / Domain | Feature / Flow Name | Functionality & User Flow | Current Status | Target Timeline
AI Engine (Phase 1) | AI Commercial Lease Deed OCR & Key Clause Extraction | AI document parser extracting monthly rent, lock-in period, rent escalation dates, and security deposit into database fields. | PENDING (AI 100%) | Day 4 (24-Oct-2026)
AI Engine (Phase 2) | AI Executive Narrative MIS Auto-Commentary Engine | LLM generating monthly executive commentary summarizing occupancy fluctuations, collections, and WALE trends. | PENDING (AI 100%) | Day 5 (25-Oct-2026)
Tenant Management | Digital Dispute Desk & Maintenance Escalation Workflow | Formal tenant dispute filing for billing or maintenance issues with photo evidence, credit notes, and resolution audit. | PENDING | Day 5 (25-Oct-2026)
FM Operations SaaS | Daily Site Activity Logging & Shift Checkpoints | Digital facility log for security shift handovers, incident reporting, and MEP patrol timestamps. | PENDING | Day 5 (25-Oct-2026)
AI Engine (Phase 3) | AI Commercial Lease Vacancy & Expiry ML Predictor | Machine learning model forecasting tenant lease renewal likelihood 180 days prior to expiry based on payment history. | PENDING (AI 100%) | Day 6 (26-Oct-2026)
AI Engine (Phase 4) | AI IoT & Equipment Predictive Maintenance Anomaly Alerts | Algorithmic anomaly detection for chiller run hours, DG fuel burn, and lift trips to trigger preventive servicing before failure. | PENDING (AI 100%) | Day 6 (26-Oct-2026)
AI Engine (Phase 5) | Tenant 24/7 AI Concierge & Smart Helpdesk Bot | Natural language assistant answering tenant queries regarding building rules, amenities, and logging maintenance tickets. | PENDING (AI 100%) | Day 6 (26-Oct-2026)
Security & Quality | End-to-End Multi-Tenant Isolation & Security Penetration Test | Verification of multi-tenant database row-level security (RLS), permission boundaries, and API token protections. | PENDING | Day 6 (26-Oct-2026)
Quality Assurance | Pre-UAT Build: Full Platform Regression Pass & Staging Hardening | Complete end-to-end regression pass across all 9 portals verifying zero console errors and clean responsive layouts. | PENDING | Day 6 (26-Oct-2026)
Platform Handover | Client UAT Demonstration Walkthrough & Production Go-Live | Interactive 45-minute staging walkthrough with leadership, production domain DNS switch, and master admin credential handover. | PENDING (SCHEDULED) | Day 7 (27-Oct-2026)
4. PENDING THIRD-PARTY INTEGRATIONS (PLANNED FOR PHASE 2 / EXTENSION) — 7 External Services (Core Platform Functions Natively)
Integration / Service | Third-Party Provider | Functional Purpose | Current Platform Native Handling | Target Delivery Phase
WhatsApp Business Cloud API / Twilio SMS | Meta / Twilio | Automated tenant rent reminder pings, OTP SMS delivery, and maintenance ticket status updates via WhatsApp. | Operates 100% natively via secure cryptographic email OTP and in-app system notification badges. | Phase 2 Extension
Razorpay Marketplace Escrow Split Payouts | Razorpay Route | Automated split payouts routing landlord rent to owner bank accounts and vendor service fees automatically. | Operates 100% natively with Razorpay Orders API for direct invoice collection & manual payout authorizations. | Phase 2 FinTech Sprint
Google Places & Geocoding API | Google Cloud Platform | Real-time address autocomplete and interactive pin drop during property onboarding and search. | Operates 100% natively with structured address entry, city/micro-market selectors, and pincode mapping. | Phase 2 Extension
Smart IoT Building Hardware Sensors | BACnet / Modbus Hardware | Direct telemetry data stream from chiller run-hour meters, DG fuel sensors, and energy sub-meters into CAM tables. | Operates 100% natively with digital sub-meter reading logs and bulk CSV import. | Phase 2 Smart Building
Biometric Turnstile & Face Kiosk SDK | Physical Access Hardware | Physical barrier flap turnstile release at building lobby when visitor scans mobile QR code. | Operates 100% natively with mobile/tablet camera QR verification desk at security desks. | Phase 2 Physical Access
Calendly 3D Virtual Tour Scheduling | Calendly / Matterport | Automated Matterport 3D walkthrough scheduling for prospective tenants directly from space detail pages. | Operates 100% natively with built-in leasing site visit request form and calendar scheduling. | Post-Launch Plug-in
Municipal Govt Fire/OC Auto-Scraper | Digilocker / Govt APIs | Automated synchronization of fire safety clearances and municipal occupancy certificates from government portals. | Operates 100% natively with Statutory Compliance Vault and automated 60/30/15-day expiry warning alerts. | Phase 2 GovTech
5. STRICT 7-DAY COMPLETION PLAN FOR WHOLE OFFICEX PLATFORM — Wednesday 21-Oct to Tuesday 27-Oct-2026
Sprint Day | Calendar Date | Platform Focus | Specific Deliverables Handled | Target Output State
Day 1 | Wednesday, 21-Oct (TODAY) | UI/UX Mobile Overhaul & Master Registers | Dashboard Mobile Drawer UX, Persistent Sidebar, Master Rent Roll Register, Approvals Console, FM Command Desk. | COMPLETED TODAY
Day 2 | Thursday, 22-Oct-2026 | Testing & QA Sign-Off Pass | Visual Stacking Plan Matrix, Approvals Maker-Checker Rules, Leasing CRM Kanban, 4-Way Compare, Calq Estimator, 52-Week PPM. | COMMITTED (Day 2)
Day 3 | Friday, 23-Oct-2026 | Automated Billing, Invoicing & Payments | Automated Rent Roll Billing Run, Utility Sub-Meters, Razorpay Gateway, RFQ Quotations Matrix, Work Orders Photo Gate. | COMMITTED (Day 3)
Day 4 | Saturday, 24-Oct-2026 | AI Phase 1, Visitor Management & Leasing Docs | AI Phase 1: Commercial Lease Deed OCR, Visitor Management QR Passes, Daily Site Activity Log, Digital LOI Generator. | COMMITTED (Day 4)
Day 5 | Sunday, 25-Oct-2026 | AI Phase 2, Compliance Vault & Dispute Desk | AI Phase 2: Executive Narrative MIS Auto-Commentary, Statutory Compliance Vault with Alerts, Digital Dispute Desk. | COMMITTED (Day 5)
Day 6 | Monday, 26-Oct-2026 | AI Phases 3–5, Security & Full Regression Pass | AI Phase 3 (Vacancy Predictor), AI Phase 4 (IoT PPM), AI Phase 5 (Tenant AI Bot), Multi-Tenant Security & Regression Pass. | COMMITTED (Day 6)
Day 7 | Tuesday, 27-Oct-2026 | Client UAT Walkthrough & Production Go-Live | Live Client UAT Demonstration Walkthrough (45 mins), Production DNS Cutover, Database Seeding & Production Go-Live Handover. | COMMITTED (Day 7 / GO-LIVE)